| Activity | Optimistic Time | Most Likely Time | Pessimistic Time | Expected Time | Variance |
| --- | --- | --- | --- | --- | --- |
| A | 10 | 22 | 22 |  |  |
| B | 20 | 20 | 20 |  |  |
| C | 4 | 10 | 16 |  |  |
| D | 2 | 14 | 32 |  |  |
| E | 8 | 8 | 20 |  |  |
| F | 8 | 14 | 20 |  |  |
| G | 4 | 4 | 4 |  |  |
| H | 2 | 12 | 16 |  |  |
| I | 6 | 16 | 38 |  |  |
| J | 2 | 8 | 14 |  |  |

Project Management Worksheet

Fill in the Expected time and Standard Deviation

Perform the Forward and Backward Passes on the network

Determine the Critical Path

What is the probability of completing the project in 46 days?  48 days?

Project Management HOMEWORK:  Problems 4 and 5 on page 430, Chapter 17

A,22

C,10

B,20

J,8

F,14

D,14

G,4

I,16

E,8

H,12